## Sheet1
Windows CE Server Based Job Ledger
Unit Rate (Rate of X) | [5 empty] | 100
Work |  | Modules | Section | Particulars |  | X | Rs. | Hr. | Remark
1 |  | Home Page | UI | Standard Kit - Custom Buttons x 2 |  | 2 | 200
|  |  |  | Standard Kit - Custom Panel |  | 0.5 | 50
|  |  |  | Standard Kit - Custom Picture Button |  | 0.5 | 50
|  |  |  | Standard Kit - Custom Label x 4 |  | 2 | 200
|  |  |  | Standard Kit - Custom Form |  | 1 | 100
|  |  | Code | Navigation Logic |  | 0 | 0
|  |  |  | Timestamp Display |  | 1 | 100
|  |  |  | Device Info. Display |  | 0 | 0
2 |  | Table Page | UI | Standard Kit - Custom Buttons x 4 |  | 4 | 400
|  |  |  | Standard Kit - Custom Panel |  | 0.5 | 50
|  |  |  | Standard Kit - Custom Picture Button |  | 0.5 | 50
|  |  |  | Standard Kit - Custom Label x 4 |  | 2 | 200
|  |  |  | Standard Kit - Custom Form |  | 0 | 0
|  |  |  | Standard Kit - Custom TextField With Label & Default Value x 2 |  | 2 | 200
|  |  | Code | Navigation Logic |  | 0 | 0
|  |  |  | Timestamp Display |  | 1 | 100
|  |  |  | Device Info. Display |  | 0 | 0
|  |  |  | Empty Field Validation |  | 1 | 100
|  |  |  | Data Save Logic |  | 0 | 0
|  |  |  | Data Clear Logic |  | 1 | 100
3 |  | Pahse Data Entry Page | UI | Standard Kit - Custom Form |  | 0 | 0
|  |  |  | Standard Kit - Custom Buttons x 2 |  | 2 | 200
|  |  |  | Standard Kit - Custom TextField With Label x 2 |  | 2 | 200
|  |  |  | Standard Kit - Custom TextField With Label & Default Value |  | 1 | 100
|  |  |  | Standard Kit - Custom Panel |  | 0.5 | 50
|  |  |  | Standard Kit - Custom Label x 4 |  | 2 | 200
|  |  | Code | Navigation Logic |  | 0 | 0
|  |  |  | Selected Phase Logic |  | 0 | 0
|  |  |  | Timestamp Display |  | 1 | 100
|  |  |  | Device Info. Display |  | 0 | 0
|  |  |  | Empty Field Validation |  | 0 | 0
|  |  |  | Field Seperator Validation |  | 0 | 0
|  |  |  | Field Format Validation |  | 0 | 0
|  |  |  | Numeric Only, Including Single Seperator TextField Implementation |  | 0 | 0
4 |  | Actions Page | UI | Standard Kit - Custom Form |  | 0 | 0
|  |  |  | Standard Kit - Custom Buttons x 4 |  | 4 | 400
|  |  |  | Standard Kit - Custom TextField With Label x |  | 3 | 300
|  |  |  | Standard Kit - Custom TextField With Label & Default Value x 2 |  | 2 | 200
|  |  | Code | Start Button Logic Inc. Timer Triggers |  | 0 | 0
|  |  |  | End Button Logic Inc. Timer Triggers |  | 0 | 0
|  |  |  | Data Pass Logic |  | 0 | 0
|  |  |  | Timer Implementation | Initilization | 0 | 0
[5 empty] | Elapsed Time Calculation | 0 | 0
[5 empty] | Elapsed Time Display | 0 | 0
|  |  |  | WS Integration | Initilize | 0 | 0
[5 empty] | Start Button WS Operation | 0 | 0
[5 empty] | Start Button WS Operation Result Manipulation | 0 | 0
[5 empty] | End Button WS Operation | 0 | 0
[5 empty] | End Button WS Operation Result Manipulation | 0 | 0
|  |  |  | Dynamic Settings Integration | Logic | 0 | 0
[5 empty] | Settings File Preperation | 0 | 0
[5 empty] | Dynamic WS URL Implementation | 0 | 0
5 |  | WS | Code | Preperation |  | 0 | 0
|  |  |  | Web Method - Insert Job |  | 0 | 0
|  |  |  | Web Method - Update Job |  | 0 | 0
|  |  |  | Data Insertion | Equipment Scrum | 0 | 0
[5 empty] | Scrum Table | 0 | 0
[5 empty] | Department | 0 | 0
[5 empty] | Time Employee | 0 | 0
[5 empty] | Work In Progress | 0 | 0
|  |  |  | Data Updation | Equipment Scrum | 0 | 0
[5 empty] | Time Employee | 0 | 0
[5 empty] | Work In Progress | 0 | 0
|  |  |  | DB Handler | Separate Connection String Implementation | 0 | 0
[5 empty] | Connection String Logic | 0 | 0
[5 empty] | Single Insert | 0 | 0
[5 empty] | Single Update | 0 | 0
6 | Env. Setup | Development System | Setup | IDE Installation |  | 0 | 0
|  |  |  | Emulator Installation | Active Sync Setup | 0 | 0
[5 empty] | Internet Configuration | 0 | 0
|  |  |  | IIS - Web Server Configuration |  | 0 | 0
|  |  |  | DB - SQL Server Installation & Configuration |  | 0 | 0
|  | Testing System | Setup | IDE Installation |  | 1 | 100
|  |  |  | Emulator Installation | Active Sync Setup | 0 | 0
[5 empty] | Internet Configuration | 0 | 0
|  |  |  | IIS - Web Server Configuration |  | 1 | 100
|  |  |  | DB - SQL Server Installation & Configuration |  | 1 | 100
7 |  | DB Design | Equipment Scrum |  |  | 0 | 0
|  |  | Scrum Table |  |  | 0 | 0
|  |  | Department |  |  | 0 | 0
|  |  | Time Employee |  |  | 0 | 0
|  |  | Work In Progress |  |  | 0 | 0
8 |  | Barcode ScanningPage | UI | Standard Kit - Custom Form |  | 0 | 0
|  |  |  | Standard Kit - Custom Label x 2 |  | 0 | 0
|  |  | Code | Selected Phase Logic |  | 0 | 0
|  |  |  | Barcode SDK Installation |  | 0 | 0
|  |  |  | Barcode SDK API Implementation | Init | 0 | 0
[5 empty] | Start Read | 0 | 0
[5 empty] | Stop Read | 0 | 0
[5 empty] | Terminate Read | 0 | 0
[5 empty] | Status Notification | 0 | 0
[5 empty] | Read Notification | 0 | 0
|  |  |  | Barcode SDK Initialize With Exception Handlers |  | 0 | 0
|  |  |  | Barcode Read Implementation With Result Manipulation & Exception Handlers |  | 0 | 0
Total | [5 empty] | 39.5 | 3950 | 0